## Gantt Chart Template
To edit this Gantt chart template, you have to make a copy on your Drive: Go to File > Make a Copy. Manage your projects with the help of GanttPRO Gantt chart software
Task name | Stard date | End date | Assigned | Status | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-02 | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-16 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-10-30 | 2022-10-31 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-13 | 2022-11-14 | 2022-11-15
Problem Statement | 2022-09-11 | 2022-09-14 | Sumanth,rohan | Done
Architectual design | 2022-09-15 | 2022-09-20 | Niranjan,Sumanth.C | Done
SRS | 2022-09-19 | 2022-09-28 | Rohan,Vinod | Done
DFD | 2022-09-29 | 2022-10-05 | Rohan,Niranjan | Done
ER Diagram | 2022-10-03 | 2022-10-12 | Vinod,Sumanth,Niranjan | Done
Use Case Diagram | 2022-10-10 | 2022-10-15 | Rohan,niranjan | Done
Implementation | 2022-10-13 | 2022-11-07 | Rohan,niranjan,vinod,sumanth | Done
testing | 2022-11-03 | 2022-11-12 | rohan,sumanth | Done

## Assignees and Status
Assignees | Status
Andrew | Open
Helen | In process
Paul | Closed
Victoria | Done
Alex